## Slide 1: Process Control Project
Institute of Information Engineering, Automation, and Mathematics
Faculty of chemical and food technology
Slovak University of Technology in Bratislava
September 26, 2022

## Slide 2: Members of SMART TEAM
Jozef Vargan
Project leader
Revision of scripts, supervision
Filip Okša
Head of the Neural Networks Department
Internal employee
Martina Bognár
Head of the Neural Networks Department
External employee

## Slide 3: Project tasks
Irrigation control implementation
On-Off control
Cooperation with Core Team
Responsible person/s – Jozef Vargan

## Slide 4: Project tasks
Irrigation control implementation
Vesna control code revision
Structural improvement of the original code
Re-evaluation of control management (time-depanding)
  switch from on-off to more advanced control (e. g. PID control)
Cooperation with App Team
Responsible person/s – Jozef Vargan (in collaboration with Filip Okša and Martina Bognár)

## Slide 5: Project tasks
Irrigation control implementation
Vesna control code revision
Neural Network SmartSensor control
Data collection and evaluation
Control implementation
Responsible person/s – Filip Okša and Martina Bognár (in collaboration with Jozef Vargan)

## Slide 6: Project tasks
Irrigation control implementation
Vesna control code revision
Neural Network SmartSensor control
Documentation
GitHub ReadMe
User manual for download
Responsible person/s – Jozef Vargan and Filip Okša and Martina Bognár

## Slide 7: Project Scheduling
1st half of the semester (2nd to 8th week)
Vesna control code revision
  Control quality verification
Neural Network SmartSensor control
  Data collection
Irrigation control implementation
Documentation
2nd half of the semester (8th to 13th week)
Vesna control code revision
  Control improvement
Neural Network SmartSensor control
  Control implementation
Documentation